## Sheet1
ID | Code | Task | Description | Predecesors | People
1 | 1 | Data Visualization of WoW Dataset |  |  | All
2 | 1.1 | Build the skeleton of the webpage |  |  | ALL
3 | 1.1.1 | Add svg obejcts for the bar/pie chart and line chart |  |  | Sam
4 | 1.1.2 | Add buttons and filter objects to webpage |  |  | Sullivan
5 | 1.1.3 | Add styling so webpage looks good |  |  | Harrison
6 | 1.2 | Have webpage read dataset |  | 2 | Sam
7 | 1.2.1 | Have webpage successfully read dataset |  |  | Sam
8 | 1.2.1.1 | Implement way to see what data is being read |  |  | Sam
9 | 1.2.2 | Have the filter options successfully filter data based off requested attributes |  | 7 | Sam
10 | 1.3 | Build functionality in bar/pie SVG |  | 6 | Sam, Sullivan
11 | 1.3.1 | Add code to have bar chart display |  |  | Sam
12 | 1.3.2 | Add code to have pie chart to display |  |  | Sullivan
13 | 1.3.3 | Add code to have webpage dynamically change with chart selection |  | 11, 12 | Sam, Sullivan
14 | 1.3.4 | Perfect Bar Chart Functionality |  | 13 | Sam
15 | 1.3.4.1 | Implement code that allows 2 different attributes to be compared |  |  | Sam
16 | 1.3.4.2 | Pass test cases | Test Cases: Check functionality with the following tuples: {level, charclass},{level, guild}, {level, race}, {level, region}, {charclass, level}… etc | 15 | Sam
17 | 1.3.5 | Perfect Pie Chart Functionality |  | 13 | Sullivan
18 | 1.3.5.1 | Implement code that allows 2 different attributes to be compared |  |  | Sullivan
19 | 1.3.5.2 | Pass test cases |  | 18 | Sullivan
20 | 1.4 | Build functionality in Line Chart SVG |  | 2 | Harrison
21 | 1.4.1 | Add code to make linechart display |  |  | Harrison
22 | 1.4.2 | Add code to allow the selction of a specific character or guild |  | 22 | Harrison
23 | 1.4.2.1 | Implement single character selection |  |  | Harrison
24 | 1.4.2.2 | Implement single guild selection |  |  | Harrison
25 | 1.4.3 | Have code properly display the character/guild over time |  | 22 | Harrison
26 | 1.4.4 | Add tooltip to display character/guild information at the specifc data point |  | 23 | Harrison
27 | 1.5 | Implement Innovative View |  | 10,20 | Sullivan
28 | 1.5.1 | figure out how to make a graph with 3 dimension |  |  | Sullivan
29 | 1.5.2 | Implement code to have a 3d graph display |  |  | Sullivan
30 | 1.5.2.1 | Pass test casses |  | 29 | ALL